## Guidance Sheet
Grant Assurance Data Return template - guidance for LAs
Which projects should I enter Information about?
This template is designed to support LAs to provide details of the projects being funded as a result of their High Needs Provision Capital Allocations (HNPCA). As we have now announced four years of HNPCA funding, LAs should endeavour to include all projects that have used HNPCA funding since 2021-22 up to 2024-25.
LAs should return their updated templates to the department by 1 October 2024 by emailing the completed template to: capital.allocations@education.gov.uk.
LAs should enter data on any known projects that will benefit from investment as a result of the their HNPCA grants. We recognise that at this stage projects may be at different stages in their delivery cycle, and may still be in the process of being fully developed (feasibility, planning, procurement etc). Recording a project on this form does not signal or create a final commitment to this project. LAs are simply requested to provide as complete a picture of intended works as possible. We recognise that not all HNPCA funding may be committed by the 1 October 2024, and therefore the template includes a record of funding that is not currently committed to a project. We would however encourage all LAs to complete the data return template to the best of their ability as this provides valuable data to the department as to the needs and the priorities of the sector in respect of High Needs capital funding, which will help inform future policy development.
If certain information might be considered locally or commercially sensitive (i.e. detailed costings for projects still in procurement or naming specific institutions where this might pre-empt local consultation), LAs should consider whether they can instead provide indicative figures or generic information (e.g. a plan to create a new SEN unit in an unidentified local secondary, pending conclusion of local consultation etc.). If LAs have any queries or concerns about the information requested, they can contact the department at capital.allocations@education.gov.uk for further information or guidance.
How to Enter Information
You can select your LA name from the drop down list in Cell D7. This will auto-populate the LA Number and HNPCA funding in the boxes below. If for any reason there is any discrepancy between this figure and the figure available on the allocations spreadsheet on GOV.UK, the published allocations spreadsheet is final.
Enter the date of completion in Cell L7.
The total amount of funding from HNPCA that your LA has committed and uncommited will auto-complete in cells M12 to M13 as you complete columns O, P, Q and R.
Please complete all yellow boxes, the template will not populate with last year's return.
The blue boxes will auto-populate information. However, if you do need to override these, please email capital.allocations@education.gov.uk and we can provide the password to unprotect the sheet.
Information on individual projects
In the section of the form indicated as Project Information please provide the requested details for each column for any projects being funded as a result of any HNPCA funding. This should include any projects funded as a result of funding allocated through the Safety Valve programme.
When you click on a yellow cell to enter data, instructions of how to enter the data will appear in a yellow box. Cells with a red tab in the corner offer more information and guidance when you hover over these cells.
Some of these fields are protected to only allow specific answers. Please select the most relevant answer from the selection available. Please do not override and provide a different answer as this may not be counted as it is more difficult to process.
Where final costings are not yet known, you may choose to provide indicative figures in the funding columns. When entering cost information please provide details of any proposed costs being met from:
a) your LA's 2021-22 HNPCA grant;
b) your LA's 2022-23 HNPCA grant;
c) your LA's 2023-24 HNPCA grant;
d) your LA's 2024-25 HNPCA grant;
e) housing developer contributions (e.g. s106, CIL); and
f) any additional proposed funding from other sources being used to support the project (e.g. from Basic Need funding, council reserves, borrowing etc.).
If the project will not be using funding from one of the above sources, please put a '0' in the relevant column.
When entering the number of places being delivered by the project, please break these down into:
a) the initial number of new High Needs places expected to be delivered by the project when it is first completed (i.e. places that didn't previously exist or were not suitable for High Needs provision);
b) the total number of new places expected to be delivered by this project once it is at full capacity; and
c) the number of places expected to be reprovided by this project. By 'reprovided places' we mean High Needs places that may have already existed, but were not suited to meet local needs (i.e. places that have been adapted, remodelled or otherwise improved to change their use, bring them up to modern standards or to meet a wider range of need).
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.
Data validation is drawn from tables on a hidden tables tab. Please do not change the tables or your data will not be consistent and we won't be able to analyse it.
Acronyms used in this return template
AP - Alternative Provision
AY - Academic Year
HN - High Needs
HNPCA - High Needs Provision Capital Allocations
LA - Local Authority
N/A - Not Applicable
PRU - Pupil Referral Unit
RP - Resourced Provision
SEN - Special Educational Needs
SPI - Special Post-16 Institution
TBC - To Be Confirmed
UTC - University Technical College

## Data Return
High Needs Provision Capital Allocations - Assurance Data Return
LAs should return this completed template to the department by 1 October 2024 by emailing the completed template to: capital.allocations@education.gov.uk. For more information on how to complete this form, please see the included Guidance Sheet.
| LOCAL AUTHORITY | Brent | [7 empty] | Date Template Completed
| LA Number | 304
| 2021-22 HNPCA Grant | 1923257.38
| 2022-23 HNPCA Grant | 5880805.56 | [7 empty] | HNPCA total funding
| 2023-24 HNPCA Grant | 6786090.03 | [7 empty] | Total funding committed | 9473257.38
| 2024-25 HNPCA Grant | 2130266.31 | [7 empty] | Total uncommitted funding | 7247161.9
Project Information
[7 empty] | Places |  |  | Types of Need |  |  | Indicative/Provisional Funding | [7 empty] | Local Consultation |  | Project delivery
Name of School or Institution | URN (If known) | School or Institution Address | Institution Type | If institution type is 'other', please provide a brief description | Ofsted Judgement | Age Range | Initial number of new HN places operational upon completion | Total number of new HN places the project will deliver once at capacity | Number of reprovided HN places | What is the primary type of need this project will address? | In addition to the primary type of need, will the project address any other types of need? | What is the main purpose of the project? (please provide additional project description in column X) | How much 2021-22 HNPCA funding will the project use? | How much 2022-23 HNPCA funding will the project use? | How much 2023-24 HNPCA funding will the project use? | How much 2024-25 HNPCA funding will the project use? | In addition to core HNPCA, how much Safety Valve funding will the project use? (This only applies to some LAs) | In addition to HNPCA, how much additional funding from housing developer contributions (s106 and CIL) will the project use? | If the project will use any other additional funding, how much funding will this be? | What is the source of this additional funding? | Have you consulted locally regarding this project? | Please give more details about what you have done as part of the consultation process | Has this project been completed? | If the project plans have slipped, why is this? | Which academic year do you anticipate the project being completed and the places being in use? | If the project is no longer going ahead, why is this? | Brief Description of Project Please briefly set out any further details of the project
Phoenix Arch School | 101581 | Drury Way, London, NW10 0NQ | Maintained Special school (including community and foundations schools) |  | Requires Improvement | Primary | 13 | 13 | 0 | Autistic Spectrum Disorder |  | Expansion of existing provision (on existing site) | 0 | 0 | 0 | 0 | 0 | 0 | 1226000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project has not yet started | Other | AY 2027/28 | N/A | The school's OFSTED went from Good to Requires Improvement. In line with the Council's School Place Planning Strategy, the Council only expands schools that are Good or Outstanding. The Council is working with the school to return to a suitable position to move forward with the project. The Council is likely to review the scope of the project pending the outcome of the impending OFSTED inspection
Elsley Primary School | 101519 | Tokyngton Avenue, Wembley, HA9 6HT | Maintained school (including community, foundation school) |  | Good | Primary | 10 | 10 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 539000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, but the project is in progress and on track | N/A | AY 2024/25 | N/A | Refurbishment of a former nursery building to create a new Additionally Resourced Provision (ARP) provision. Works are on site and the building will be ready for early AY 24/25
Wembley Primary School | 130095 | East Lane, Wembley, HA9 7NW | Maintained school (including community, foundation school) |  | Good | Primary | 0 | 0 | 0 | Autistic Spectrum Disorder |  | New facility within an existing provision | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | The project is no longer going ahead | N/A |  | Other | School withdrew from arrangements. Funding was reallocated to other projects.
Woodfield School | 140796 | Glenwood Avenue, Kingsbury, London, NW9 7LY | Academy or free school - Special |  | Outstanding | Secondary | 40 | 40 | 0 | Autistic Spectrum Disorder |  | Expansion of existing provision (existing site) | 0 | 0 | 0 | 0 | 0 | 0 | 3950000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Site was not viable | AY 2027/28 | N/A | Expansion of the school by 40 places. The Council is still considering feasibility options for the expansion and expect to proceed with the designs this AY
The Village School | 146212 | Grove Park, Kingsbury, London, NW9 0JY | Academy or free school - Special |  | Outstanding | Primary, secondary and post-16 | 20 | 20 | 60 | Autistic Spectrum Disorder |  | Expansion of existing provision (on satellite site) | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project has not yet started | Site was not viable | AY 2027/28 | N/A | Expansion of the school by 20 places and re-provision of 60 places. Proposed build options not viable and so Council is reviewing options on delivering this project
Manor School | 144053 | Chamberlayne Road, Kensal Rise, London, NW10 3NT | Academy or free school - Special |  | Outstanding | Primary | 34 | 54 | 0 | Autistic Spectrum Disorder |  | Expansion of existing provision (on satellite site) | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | Basic Need Funding | Consultation completed |  | Yes, the project has been completed | N/A | AY 2023/24 | N/A | Project completed in 23/24 as a temporary expansion
St Gregory's Catholic Science College | 142560 | Donnington Road, Kenton, Harrow, HA3 0NB | Academy or free school - Mainstream |  | Outstanding | Secondary and post-16 | 14 | 28 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 1872000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project has not yet started | Other | AY 2027/28 | N/A | Discovery of RAAC and now school part of SRP poject. ARP to be part of new build of school
St Gregory's Catholic Science College | 142560 | Donnington Road, Kenton, Harrow, HA3 0NB | Academy or free school - Mainstream |  | Outstanding | Secondary and post-16 | 0 | 0 | 0 | Physical Disability |  | Accessibility | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | Basic Need Funding |  |  | The project is no longer going ahead | N/A |  | Other | Discovery of RAAC and now school part of SRP project to rebuild the school
Salusbury Primary | 101527 | Salusbury Road, Kilburn, London, NW6 6RG | Maintained school (including community, foundation school) |  | Good | Primary | 0 | 0 | 0 | Physical Disability |  | Accessibility | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | Basic Need Funding | N/A |  | Yes, the project has been completed | N/A | AY 2023/24 | N/A | Installation of lift to improve accessibility at the school. Works complete
Mount Stewart Infant School | 101501 | Carlisle Gardens, Mount Stewart Avenue, Kenton, Harrow, HA3 0JX | Maintained school (including community, foundation school) |  | Good | Primary | 7 | 21 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 1643000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Other |  | N/A | School reconsidering whether to provide ARP or not
St Margaret Clitherow RC Primary School | 146179 | Quainton Street, London, NW10 0BG | Academy or free school - Mainstream |  | Not yet inspected | Primary | 7 | 10 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 1371000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Difficulties in procuring work/delays in construction | AY 2025/26 | N/A | New ARP provision. Initial contractor procurement exercise was unsuccessful. New contractor now appointed to complete design and expects to complete ready for AY 25/26
Newman Catholic College | 101564 | Harlesden Road, Brent, London, NW10 3RN | Other school |  | Good | Secondary and post-16 | 21 | 21 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 1675000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Difficulties in procuring work/delays in construction | AY 2025/26 | N/A | New ARP provision. Initial contractor procurement exercise was unsuccessful. New contractor now appointed to complete design and expects to complete ready for AY 25/26
Newfield Primary School | 101522 | Longstone Avenue, Willesden, London, NW10 3UD | Maintained school (including community, foundation school) |  | Good | Primary | 7 | 15 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 366000 | Basic Need Funding | Consultation completed |  | Yes, the project has been completed | N/A | AY 2023/24 | N/A | Refurbishment of a former nursery building to create a new Additionally Resourced Provision (ARP) provision. Works are complete
Preston Park Primary School | 101510 | College Road, Wembley, HA9 8RJ | Maintained school (including community, foundation school) |  | Good | Primary | 14 | 14 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 1679000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Difficulties in procuring work/delays in construction | AY 2025/26 | N/A | New ARP provision. Initial contractor procurement exercise was unsuccessful. New contractor now appointed to complete design and expects to complete ready for AY 25/26
New SEN School |  | London Road, Wembley HA9 7EU | Academy/free school - Special |  | This institution is not yet open | Secondary | 150 | 150 | 0 | Autistic Spectrum Disorder |  | Entirely new LA presumption route school | 1923257.38 | 3800000 | 0 | 0 | 0 | 0 | 18076742.62 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, but the project is in progress and on track | N/A | AY 2025/26 | N/A | New 150 place SEND school. Contractor on site and expected to complete AY 25/26
Queen Park Community School | 138609 | Aylestone Avenue, London, NW6 7BQ | Academy/free school - Mainstream |  | Good | Secondary | 25 | 25 | 0 | Autistic Spectrum Disorder |  | Entirely new SEN unit within a school | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | Basic Need Funding | Consultation in progress | Comprehensive engagement in 2021-22 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Other | AY 2026/27 | N/A | New ARP provision. Initial school led design work reviewed and now Council taking on responsibility for delivering project. Design work underway with new design team
Post-16 Skills Resource Centre and Horticultural Centre (in development) |  | Birchen Grove, London, NW9 8RY | SPI (Special Post-16 Institution) |  | This institution is not yet open | Post-16 |  |  |  | Other (please provide details in project description) |  | Other (please provide details in project description) | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 |  | Consultation in progress | Comprehensive engagement in 2022-2023 with parents/carers young people and schools. Further consultation to be undertaken with schools and local community as part of the design process and planning application process. | No, the project is in progress but has slipped against original plans | Costs of the project were higher than anticipated | AY 2026/27 | N/A | Horticulture centre approved by Cabinet. Consultants appointed and design work underway
Inclusive Environments |  | Multiple Schools |  |  |  | Primary and secondary |  |  |  | Other (please provide details in project description) |  | Improvement of an existing provision | 0 | 750000 | 0 | 0 | 0 | 0 | 0 |  | N/A |  | No, but the project is in progress and on track | N/A | AY 2024/25 | N/A | This project relates to making a number of accessibility and inclusivity enhancements to several schools to allow for pupils with EHCPs to have access to support required
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.
Note on O20: Where final costings are not yet known, you may choose to provide indicative figures in the funding columns. Recording information on this form does not signal or create a final commitment, but we do ask that LAs return the template to the best of their ability.
Note on D21: For new projects, the address of the site may not yet be confirmed. If there is a proposed/likely site address, please use this. If not, this column may be left blank.
Note on K21: Reprovided places refer to existing places that will continue to be delivered and will benefit from the project.
Note on N21: More details/examples: - Entirely new school - Entirely new SEN unit within a school - Expansion of existing provision (e.g. additional places created through a new classroom) - Improvement of an existing provision (e.g. new equipment) - New facility within an existing provision (e.g. sensory room or changing facility) - Adapting existing provision to meet different needs - Accessibility - Other (please provide details in project description)
Note on U21: This does not include housing developer contribitions (which can be added to column T). Additional funding sources may include Basic Need funding, council reserves, borrowing etc.

## Tables (hidden)
|  | 2021-22 ALLOCATION | 2022-23 ALLOCATION | 2023-24 ALLOCATION | 2024-25 ALLOCATION
SELECT INSTITUTION TYPE
- | SELECT LOCAL AUTHORITY |  |  |  |  | Independent school | Ofsted inspection judgment | Age Range
301 | Barking and Dagenham | 2159812.71 | 9181089.37 | 5067365.61 | 1093807.65 | 16-19 Academy/free school | Outstanding | Under 5s
302 | Barnet | 2928936.6 | 10104935 | 6685996.64 | 1675023.9 | Academy/free school - Special | Good | Primary
370 | Barnsley | 1460729.06 | 5714239.13 | 4492168.73 | 1261774.04 | Academy/free school - Mainstream | Requires Improvement | Secondary
800 | Bath and North East Somerset | 726954.52 | 4551454.16 | 6903801.98 | 611083.37 | AP - Academy or free school | Inadequate | Primary and secondary
822 | Bedford Borough | 517417.54 | 3160879.3 | 2985935.56 | 736462.72 | AP - PRU (LA maintained) | This institution is not inspected by Ofsted | Post-16
303 | Bexley | 956587.48 | 4062810.94 | 15138051.54 | 1765862.8 | LA nursery school | This institution is open, but has not yet been inspected by Ofsted | Secondary and post-16
330 | Birmingham | 6500323.78 | 21688399.74 | 17731902.03 | 4940122.7 | Maintained school | This institution is not yet open | Primary, secondary and post-16
889 | Blackburn with Darwen | 500000 | 2342618.75 | 2550921.36 | 719973.39 | Maintained Special school | This institution is still to be determined | Other category in 0-25 age-range (please specify in project description)
890 | Blackpool | 500000 | 1464529.14 | 8174736.8 | 634305.99 | Non-Maintained Special School
350 | Bolton | 1327440.51 | 15364796.24 | 4474654.43 | 1298937.12 | Other nursery or early years provision
839 | Bournemouth, Christchurch and Poole | 2365961.51 | 9213326.35 | 5894586.3 | 1341728.33 | Other school |  | Secondary Type of Need
867 | Bracknell Forest | 500000 | 2725564.43 | 2473486.47 | 4623311.73 | Other sixth-form or FE college |  | No - The project will only address its primary type of need
380 | Bradford | 2144168.48 | 9232723.15 | 8869160.4 | 2433636.15 | Special unit/ RP at academy | Primary Type of Need | Yes - The project will address a range of other needs
304 | Brent | 1923257.38 | 5880805.56 | 6786090.03 | 2130266.31 | Special unit/ RP at free school | Autistic Spectrum Disorder | Yes - Autistic Spectrum Disorder
846 | Brighton and Hove | 1029704.8 | 4706298.11 | 3516201.74 | 849323.16 | Special unit/ RP at LA maintained school | Hearing Impairment | Yes - Hearing Impairment
801 | Bristol, City of | 1840832.33 | 11270922.68 | 6727453.54 | 14470505.23 | Special unit/ RP at other school | Moderate Learning Difficulty | Yes - Moderate Learning Difficulty
305 | Bromley | 2450780.28 | 6651669.96 | 6165963.93 | 1764938.28 | SPI (Special Post-16 Institution) | Multi- Sensory Impairment | Yes - Multi- Sensory Impairment
825 | Buckinghamshire | 3555125.39 | 11121278.56 | 9860063.34 | 2797448.43 | Studio school | Other (please provide details in project description) | Yes - Other (please provide details in project description)
351 | Bury | 4370946.66 | 2931468.09 | 3550642.98 | 1077227.05 | University technical college | Physical Disability | Yes - Physical Disability
381 | Calderdale | 551745.88 | 3422213.36 | 2214505.54 | 607364.65 |  | Profound & Multiple Learning Difficulty | Yes - Profound & Multiple Learning Difficulty
873 | Cambridgeshire | 2709339.06 | 22581378.82 | 9104835.14 | 2352233.2 | Main Purpose of Project | Severe Learning Difficulty | Yes - Severe Learning Difficulty
202 | Camden | 2659040.41 | 8639919.17 | 3243472.99 | 456024.45 | Entirely new free school | Social, Emotional and Mental Health | Yes - Social, Emotional and Mental Health
823 | Central Bedfordshire | 1940603.89 | 8760302.88 | 6687071.18 | 1701826.9 | Entirely new LA presumption route school | Specific Learning Difficulty | Yes - Specific Learning Difficulty
895 | Cheshire East | 1263815.33 | 7214677.56 | 5744443.81 | 18251968.28 | Entirely new SEN unit within a school | Speech, Language and Communication | Yes - Speech, Language and Communication
896 | Cheshire West and Chester | 1079140.93 | 5698026.42 | 4700460.85 | 1236794.08 | Expansion of existing provision (existing site) | Visual Impairment | Yes - Visual Impairment
201 | City of London | 0 | 0 | N/A | N/A | Expansion of existing provision (satellite site)
908 | Cornwall | 2442128.57 | 11147439.51 | 9727957.96 | 2804639.5 | Improvement of an existing provision
331 | Coventry | 2426212.34 | 10518024.69 | 6776584.34 | 1686577.16 | New facility within an existing provision
306 | Croydon | 1583319.34 | 5578111.89 | 6043026.32 | 1839744.92 | Adapting existing provision to meet different needs
942 | Cumberland | N/A | N/A | 4387643.04 | 949593.93 | Accessibility | Anticipated completion | Has the project been completed?
909 | Cumbria | 753286.89 | 2672619.17 | N/A | N/A | Other (please provide details in project description) |  | Yes, the project has been completed
841 | Darlington | 500000 | 1736535.73 | 1498065.03 | 463367.27 |  | AY 2021/22 | No, but the project is in progress and on track
831 | Derby | 1565260.46 | 7274447.9 | 5863036.38 | 1640408.57 |  | AY 2022/23 | No, the project is in progress but has slipped against original plans
830 | Derbyshire | 2489980 | 10179536.29 | 13242601.34 | 4204819.41 |  | AY 2023/24 | No, the project has not yet started
878 | Devon | 2145040.68 | 12790568.34 | 12965577.06 | 3772852.11 |  | AY 2024/25 | The project is no longer going ahead
371 | Doncaster | 1064926.66 | 5502839.49 | 5543010.11 | 1614401.75 |  | AY 2025/26
838 | Dorset | 500000 | 4901989.18 | 5743828.05 | 12297935.22 |  | AY 2026/27 | If project has been cancelled
332 | Dudley | 1416043.37 | 6707208.5 | 5877397 | 1718054.1 | Local consultation | AY 2027/28 | N/A
840 | Durham | 2354865.22 | 8510183.33 | 7805806.52 | 2063484.65 | Consultation completed | AY 2028/29 | Funding needed to be prioritised elsewhere
307 | Ealing | 2298819.98 | 6825163.98 | 6754992.16 | 1942886.19 | Consultation in progress | AY 2029/30 | Costs of the project were higher than anticipated
811 | East Riding of Yorkshire | 746801.38 | 4918860.25 | 5156632.27 | 1506106.43 | Consultation planned, but not yet started | Beyond 2030 | Site was not viable
845 | East Sussex | 1273987.46 | 6726770.93 | 6932116.44 | 1935934.37 | TBC | NA | The need for places has changed
308 | Enfield | 1317955.79 | 4485182.52 | 7686580.44 | 2466314.46 | N/A |  | Other
881 | Essex | 5238295.05 | 19345531.04 | 20732949.06 | 5685293.86
390 | Gateshead | 1343333.38 | 3492238.28 | 2063527.53 | 489679.71 |  |  | If the project plans have slipped, why is this?
916 | Gloucestershire | 1988464.83 | 10990306.73 | 8937337.59 | 2280409.91 |  |  | N/A
203 | Greenwich | 2784606.77 | 10020102.81 | 6442424.29 | 1322188.6 |  |  | Funding needed to be prioritised elsewhere
204 | Hackney | 2724671.29 | 10083307.6 | 5105975.4 | 984214.91 |  |  | Costs of the project were higher than anticipated
876 | Halton | 500000 | 2666386.97 | 2198924.32 | 626655.48 |  |  | Site was not viable
205 | Hammersmith and Fulham | 2329829.59 | 4801556.14 | 2242432.59 | 390645.27 |  |  | Difficulties in procuring work/delays in construction
850 | Hampshire | 6789279.35 | 25243509.04 | 24835932.48 | 7621972.65 |  |  | Other
309 | Haringey | 1023937.98 | 9339911.81 | 3364919.1 | 1080832.51
310 | Harrow | 821789.71 | 4138547.45 | 5219519.43 | 1407784.88
805 | Hartlepool | 500000 | 1384647.48 | 975805.18 | 270604.69
311 | Havering | 2206149.31 | 7670580.12 | 5675974.72 | 1289438
884 | Herefordshire | 648121.72 | 2611683.04 | 2819829.82 | 823167.22
919 | Hertfordshire | 4761202.95 | 20007920.5 | 18331544.53 | 4710765.17
312 | Hillingdon | 2872215.63 | 15090653.15 | 6120161.02 | 1505204.77
313 | Hounslow | 2419088.63 | 9508908.73 | 7156678.31 | 1961385.1
921 | Isle of Wight | 500000 | 1050083.77 | 1087841.01 | 356205.65
420 | Isles of Scilly | 500000 | 788074.51 | 211925.49 | 500000
206 | Islington | 1834418.8 | 5638378.53 | 3015407.85 | 559637.22
207 | Kensington and Chelsea | 2383501.3 | 7461394.79 | 3059324.53 | 270788.92
886 | Kent | 6638936.62 | 32108713.21 | 29001569.25 | 7980358.94
810 | Kingston Upon Hull, City of | 1488666.89 | 7192376.88 | 5389726.66 | 1488209.7
314 | Kingston upon Thames | 5114646.33 | 5540177.8 | 3176269.06 | 715027.93
382 | Kirklees | 1609971.75 | 15861570.56 | 6977510.55 | 2040132.19
340 | Knowsley | 509167.24 | 3890300.75 | 2859035.28 | 760081.74
208 | Lambeth | 2541861.32 | 4855965.19 | 3380219.86 | 845627.71
888 | Lancashire | 4724149.55 | 20178483.14 | 19581598.78 | 5559078.56
383 | Leeds | 4574287.88 | 22576594.86 | 11734902.24 | 2321304.59
856 | Leicester | 2013815.67 | 8420348.51 | 5436624.97 | 1290550.8
855 | Leicestershire | 3641554.5 | 12735106.2 | 11759690.01 | 3248168.87
209 | Lewisham | 2550162.94 | 8052934.31 | 5499203.4 | 1337033.13
925 | Lincolnshire | 2986063.27 | 12901062.56 | 12370059.38 | 3434621.64
341 | Liverpool | 3460315.08 | 14301620.34 | 7045886.16 | 1373537.2
821 | Luton | 1243963.04 | 4313023.04 | 3206488.37 | 845667.16
352 | Manchester | 2323799.63 | 12710172.23 | 9429499.48 | 2323156.39
887 | Medway | 1939762.41 | 13540524.23 | 5482269.01 | 1574935.68
315 | Merton | 2192304.74 | 13585092.28 | 4344501.44 | 1233921.71
806 | Middlesbrough | 1159882.3 | 3848136.66 | 2319833.7 | 471911.54
826 | Milton Keynes | 2971552.17 | 10132199.9 | 5546021.24 | 1088334.89
391 | Newcastle upon Tyne | 1461608.45 | 7010093.85 | 4113624.62 | 753678.03
316 | Newham | 2611716.38 | 7296290.68 | 8494621.03 | 2728149.17
926 | Norfolk | 4393596.96 | 14928082.7 | 11853823.34 | 3034143.12
812 | North East Lincolnshire | 883215.54 | 2796066.49 | 1741727.99 | 458089.8
813 | North Lincolnshire | 729278.21 | 3002092.99 | 2992572.67 | 854468
940 | North Northamptonshire | 1296620.5058 | 7137774.67 | 6803123.52 | 1844172.91
802 | North Somerset | 1152776.08 | 3260036.66 | 6919418.33 | 1159472.33
392 | North Tyneside | 663431.61 | 2971475.43 | 6926139.22 | 557991.51
815 | North Yorkshire | 716840.2 | 6543369.57 | 7491930.42 | 2264233.5
929 | Northumberland | 851301.82 | 2665635.95 | 3978192.25 | 1195442.7
892 | Nottingham | 2550244.97 | 11973140.92 | 5985535.04 | 1035259.4
891 | Nottinghamshire | 5316391.06 | 19988078.32 | 16548153.29 | 4629822.83
353 | Oldham | 830008.86 | 3924992.4 | 3396522.64 | 862005.91
931 | Oxfordshire | 3520938.22 | 11987215.81 | 10121255.12 | 2620535.16
874 | Peterborough | 1777784.42 | 7049175.33 | 3777067.11 | 791525.27
879 | Plymouth | 1447787.32 | 6956768.68 | 4505429.14 | 977733.39
851 | Portsmouth | 1181280.62 | 4559375.47 | 2800951.5 | 632119.6
870 | Reading | 954776.21 | 3857086.57 | 3229083.47 | 857535.13
317 | Redbridge | 1847655.81 | 8564467.2 | 5629640 | 1228177.41
807 | Redcar and Cleveland | 807275.48 | 1608840.55 | 1620911.02 | 369088.86
318 | Richmond upon Thames | 6134035.28 | 6926302.6 | 4817630.2 | 1067542.44
354 | Rochdale | 1156818.5 | 5268703.92 | 4943824.78 | 1467113.33
372 | Rotherham | 1059889.81 | 9228873.48 | 3752187.08 | 1002745.16
857 | Rutland | 500000 | 810549.76 | 653392.07 | 172805.84
355 | Salford | 2467910.75 | 10206097.65 | 5055669.69 | 772198.76
333 | Sandwell | 1488855.05 | 6868024.9 | 5753081.72 | 1485421.55
343 | Sefton | 675523.94 | 3737877.68 | 4602768.42 | 1370441.57
373 | Sheffield | 1944425.94 | 10830418.13 | 6805547.35 | 1538633.19
893 | Shropshire | 500000 | 3875585.98 | 4126723.33 | 1141085.94
871 | Slough | 2065765.64 | 5297676.02 | 3850624.22 | 1055806.46
334 | Solihull | 1055762.06 | 4910941.3 | 3826993.47 | 1000250.26
933 | Somerset | 983283.28 | 7683078.75 | 9393696.19 | 2797769.09
803 | South Gloucestershire | 1908231.29 | 8377976.54 | 6249892.6 | 1583333.42
393 | South Tyneside | 632130.41 | 2559951.67 | 1951861.38 | 517220.91
852 | Southampton | 2106601.46 | 7602038.55 | 4424276.2 | 980954.63
882 | Southend-on-Sea | 1061569.94 | 4770879.63 | 2411737.52 | 557610.05
210 | Southwark | 1306335.56 | 9515182.17 | 5957728.84 | 1697691.64
342 | St Helens | 649444.03 | 3242266.7 | 2144123.21 | 525512.49
860 | Staffordshire | 2441299.98 | 10278776.55 | 11760528.56 | 3558948.25
356 | Stockport | 1274115.32 | 5243398.76 | 4656283.24 | 1350642.5
808 | Stockton-on-Tees | 876119.04 | 3458089.77 | 2936671.69 | 736430.18
861 | Stoke-on-Trent | 10199220.46 | 5410992.99 | 5208986.52 | 1491835.7
935 | Suffolk | 2111925.19 | 9381620.67 | 10758718.22 | 3156716.74
394 | Sunderland | 520782.55 | 4280724.63 | 3893510.81 | 1154532.96
936 | Surrey | 6920304.22 | 29572648.76 | 19915638.18 | 5391703.52
319 | Sutton | 1924542.49 | 6430671.29 | 3370191.61 | 824740.11
866 | Swindon | 1598452.1 | 5996536.64 | 3917519.58 | 989736.57
357 | Tameside | 1223336.11 | 5732980.3 | 4865994.02 | 1371829.21
894 | Telford and Wrekin | 1303857.87 | 4401129.98 | 3798337.84 | 1062775.27
883 | Thurrock | 678526 | 4487808.58 | 2994414.65 | 654821.29
880 | Torbay | 530149.55 | 2076643.91 | 2011175.75 | 576354.5
211 | Tower Hamlets | 2638807.37 | 10507823.99 | 5217690.92 | 1053093.72
358 | Trafford | 1676744.46 | 6849264.81 | 4542907.24 | 1213129.43
384 | Wakefield | 1473875.94 | 6076097.78 | 6106417.85 | 1834798.64
335 | Walsall | 1419381.97 | 7227924.29 | 6091965.42 | 1724970.86
320 | Waltham Forest | 1434725.15 | 5514062.59 | 3848027.46 | 1001073.59
212 | Wandsworth | 4837414.07 | 15827055.42 | 6015457.03 | 753530.44
877 | Warrington | 710210.47 | 2727753.24 | 3144056.6 | 1001367.15
937 | Warwickshire | 2747759.95 | 9583082.43 | 7533184.49 | 2027958.72
869 | West Berkshire | 500000 | 2651580.15 | 2298724.34 | 496819.17
941 | West Northamptonshire | 1522119.7242 | 10900195.92 | 8080272.71 | 2132850.49
938 | West Sussex | 4095781.27 | 16479349.06 | 14403828.5 | 3998703.82
943 | Westmorland and Furness | 1040039.03 | 4523712.16 | 2964348.24 | 649082.76
213 | Westminster | N/A | N/A | 4041095.41 | 987532.01
359 | Wigan | 1625569.97 | 5585450.33 | 5162254.91 | 1526636.99
865 | Wiltshire | 2055333.02 | 6753045.92 | 8630681.55 | 2591775.7
868 | Windsor and Maidenhead | 500000 | 2406905.31 | 1870043.63 | 429329.26
344 | Wirral | 1046545.72 | 4390504.05 | 4092751.09 | 1209682
872 | Wokingham | 1266317.22 | 5634050.45 | 9578819.9 | 797168.4
336 | Wolverhampton | 2254086.99 | 5808551.94 | 3876746.81 | 886241.34
885 | Worcestershire | 1539043.81 | 8408559.81 | 8187337.66 | 2394959.65
816 | York | 627439.06 | 7056626.19 | 2270412.45 | 451093.47