## in
reference | plan | plan-event | event-date | actual-date | entry-date | notes
london-borough-of-brent-new-local-plan-publish-notice-intention-commence | london-borough-of-brent-new-local-plan | publish-notice-intention-commence | 30/06/2026 | 30/06/2026 | 29/06/2026
london-borough-of-brent-new-local-plan-scoping-consultation-start | london-borough-of-brent-new-local-plan | scoping-consultation-start | 2026-02-09 | 2026-02-09 | 2026-02-09
london-borough-of-brent-new-local-plan-scoping-consultation-end | london-borough-of-brent-new-local-plan | scoping-consultation-end | 30/09/2026 | 30/09/2026 | 2026-02-09
london-borough-of-brent-new-local-plan-gateway-1-self-assessment | london-borough-of-brent-new-local-plan | gateway-1-self-assessment | 30/10/2026 |  | 30/10/2026
london-borough-of-brent-new-local-plan-plan-content-evidence-consultation-start | london-borough-of-brent-new-local-plan | plan-content-evidence-consultation-start | 2026-07-27 |  | 29/06/2026
london-borough-of-brent-new-local-plan-plan-content-evidence-consultation-end | london-borough-of-brent-new-local-plan | plan-content-evidence-consultation-end | 2026-07-27 |  | 29/06/2026
london-borough-of-brent-new-local-plan-gateway-2-advice-sought | london-borough-of-brent-new-local-plan | gateway-2-advice-sought | 2026-10-27 |  | 29/06/2026
london-borough-of-brent-new-local-plan-gateway-2-advice-published | london-borough-of-brent-new-local-plan | gateway-2-advice-published | 2026-11-27 |  | 29/06/2026
london-borough-of-brent-new-local-plan-proposed-plan-consultation-start | london-borough-of-brent-new-local-plan | proposed-plan-consultation-start | 2026-05-28 |  | 29/06/2026
london-borough-of-brent-new-local-plan-proposed-plan-consultation-end | london-borough-of-brent-new-local-plan | proposed-plan-consultation-end | 2026-05-28 |  | 29/06/2026
london-borough-of-brent-new-local-plan-gateway-3-advice-sought | london-borough-of-brent-new-local-plan | gateway-3-advice-sought | 2026-08-28 |  | 29/06/2026
london-borough-of-brent-new-local-plan-gateway-3-advice-published | london-borough-of-brent-new-local-plan | gateway-3-advice-published | 2026-09-28 |  | 29/06/2026
london-borough-of-brent-new-local-plan-examination-submitted | london-borough-of-brent-new-local-plan | examination-submitted | 2026-11-28 |  | 29/06/2026
london-borough-of-brent-new-local-plan-examination-recommendations-published | london-borough-of-brent-new-local-plan | examination-recommendations-published | 2026-12-28 |  | 29/06/2026
london-borough-of-brent-new-local-plan-main-modification-consultation-start | london-borough-of-brent-new-local-plan | main-modification-consultation-start | 2029-02-01 |  | 29/06/2026
london-borough-of-brent-new-local-plan-main-modification-consultation-end | london-borough-of-brent-new-local-plan | main-modification-consultation-end | 2029-02-01 |  | 29/06/2026
london-borough-of-brent-new-local-plan-adopted | london-borough-of-brent-new-local-plan | adopted | 2026-04-29 |  | 29/06/2026