## WSoA actions
Written Statement of Action Monitoring Dashboard 14 June 2018
WSoA1 100% done, 0% in progress, 0% not started
WSoA2 100% done, 0% in progress, 0% not started
WSoA3 100% done, 0% in progress, 0% not started
WSoA4 80% done, 20% in progress, 0% not started
WSoA5 100% done, 0% in progress, 0% not started
| Key Actions | Lead | Objective | Target Date | Progress | Progress milestones and evidence
Black = incomplete action, green = evidence of completed action, blue = follow-on activity
WSoA1 100% done, 0% in progress, 0% not started | Strengthen CCG leadership in implementing the SEND reforms | CCG Dionne Greenaway Senior Commissioning Manager Duncan Ambrose Assistant Director Dr Sarah Basham Vice Chair | A) Update SEND strategic plan to ensure CCG Chair and Chief Officer have oversight of actions to deliver SEND reforms | Target: Wednesday 19 Jul'17 Achieved: Wednesday 16 Aug'17 | Done | Draft strategic plan shared at Brent Children's Trust, Jul'17. CCG Executive Committee agreed strategic plan Jul'17. Shared with NHS England London Regional Lead for SEND, Aug'17. Updated SEND plan shared with CCG Integrated Governance Committee 16 Aug'17. | 1 | 100 | 100
|  | CCG Dionne Greenaway Senior Commissioning Manager | B) Appoint a Designated Clinical Officer (DCO) to support the CCG implement SEND reforms | Target: Friday 29 Sep'17 Achieved: Friday 29 Sep'17 | Done | DCO substantive post agreed May'17. Brent CCG agreed 0.6 FTE role designed to complement existing paediatrician reviewing 0-18s EHCPs, and CCG-LD clinical lead. Post to be shared with Harrow CCG and Hillingdon CCG. May'17 DCO recruitment unsuccessful. Role development discussed with existing NWLCCG DCOs, and agreed NWLCCG peer reviews 13 July '17. Substantive budget confirmed in review of CCG staffing, Aug'17. Role development discussed with NHS England London Regional Lead for SEND 11 Aug '17. Re-advertised Aug'17, interview 06 Sep'17. Interim recruitment confirmed 22 Aug'17, candidates identified and available. Invitation to pan-London DCO/DMO meeting. DCO linked into NHS England London Regional Lead for SEND 14 Sep '17 Interim in post 29 Sep'17, to allow 3 months cover during substantive notice period. Interim post holder confirmed as substantive DCO 29 Sep '17. Substantive DCO in post 11 Dec'17. | 0 | 0 | 0 | In progress
|  | CCG Duncan Ambrose Assistant Director Sheik Auladin Chief Operating Officer | C) CCG leaders work with the Corporate Management Team of Brent Council to establish closer formal working arrangements between CCG and council in commissioning SEND. Strengthen CCG leadership within Brent Children’s Trust to ensure CCG commissioned health aspects are adequately considered and represented, and to give mutual support and challenge of statutory duty compliance. Terms of Reference of the Children's Trust review, to consider extending membership to health providers. | Target: Wednesday 01 Nov'17 Achieved: Friday 15 Dec'17 | Done | CCG statutory duties summarised clearly as part of the planning process 14 Jul'17. Senior CCG and Council officers developed joint WSoA and dashboard. CCG Accountable Officer, CCG Chief Operating Officer, Brent Council Chief Executive, and Brent Council Strategic Director, Children and Young People confirmed high level CCG commitment to implementing the SEND reforms, 07 Aug'17. Joint monitoring at Brent Children's Trust started, 12 Sep'17. Reporting on WSoA to Health and Wellbeing Board 05 Oct'17. Health and Wellbeing Board recommended senior representation from North West London Healthcare Trust. Assurance on progress via Community and Wellbeing Scrutiny Committee 22 Nov'17. Review of Children's Trust Terms of Reference 15 Dec '17, for Jan'18 Children's Trust. Case study evaluation by DCO demonstrating the CCG leadership action and impact through the Children's Trust, circulated to CCG Senior Management Team 15 Dec '17.
|  | CCG Duncan Ambrose Assistant Director | D) CCG leaders will attend Brent Parent/Carer forum to ensure strong partnership leadership of parent/carer engagement and co-production from 01 September 2017. | Target: Friday 01 Oct'17 Achieved: Monday 27 Nov'17 | Done | CCG attended Brent Parent/Carer Forum 14 Sep'17 to consult on Written Statement of Action. Vision for future delivery co-produced with attendees and included in WSoA. CCG led co-production events 21 Sep'17 well attended by parents. CCG-led and jointly facilitated with Brent Council Health Partners Forum 18 Oct'17. Joint Brent CCG and Brent Council strategic planning day to co-produce with parents and carers a refreshed joint SEND strategy, first session 27 Nov'17.
WSoA2 100% done, 0% in progress, 0% not started | Implement joint commissioning arrangements to prevent gaps between services | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion | A) Establish new joint commissioning post to support SEND and CAMHS improvements | Target: Friday 15 Sep'17 Achieved: Friday 15 Sep'17 | Done | Joint funding confirmed and job description agreed, 25 Jul'17. CCG leading substantive recruitment, 08 Aug'17. Brent Council led interim recruitment, out to advert, 18 Aug'17. Interim appointment made 15 Sep'17. Interviews and appointment for permanent post 29 Sep '17. Quality check of children's services joint commisisoning arrangements through EY option appraisal completed 11 Dec '17 | 1 | 100 | 100 | Done
|  | CCG Dionne Greenaway Senior Commissioning Manager Duncan Ambrose Assistant Director Dr Sarah Basham Vice Chair LA Sandra Bingham Head of Inclusion Brian Grady Operational Director | B) Joint Brent CCG and Brent Council strategic planning day to co-produce with parents and carers a refreshed joint SEND strategy in October 2017. | Target: Tuesday 31 Oct'17 Achieved: Wednesday 18 Oct'17 | Done | Brent Council SEND strategy 2014-2017 and Brent CCG strategic review document 2017 used to prepare refresh engagement events in Sep'17 and Oct'17. Parent/Carer engagement events have informed priorities. Feedback given to parents on progress of strategy at Health Partners Forum, 18 Oct'17. Three formal governance meetings held in October and November to coproduce the next SEND strategy (Joint Commissioning Group, the Joint commisisoning workstream and the Inclusion Strategic Board), with Parent/Carers as members. Agreement of joint SEND strategy by CT Joint Commissioning Group 10 Apr '18 | 0 | 0 | 0 | In progress
|  | CCG Sheik Auladin Chief Operating Officer LA Gail Tolley Strategic Director (DCS) | C) Establish closer formal working arrangements between CCG and LA in commissioning SEND | Target: Wednesday 22 Nov'17 Achieved: Wednesday 10 Jan'18 | Done | ITT developed for scope of joint CCG-Council commissioning teams for SEND 07 Aug'17. Joint Contract Monitoring established Aug' 17 CCG Chief Officer and Chief Operating Officer discussed with Brent Council Chief Executive and Strategic Director, Children and Young People 07 Aug'17. Agreement from both Council and CCG to integrate commissioning of SEND services. Potential for integrated commissioning arrangements to be broadened to cover other service areas in the future. EY completed baseline commissioning structure options appraisal 14 Aug'17. Development of joint commissioning structures launched Aug '17 with evaluation Sep '17 Joint commissioning structure options considered and structure agreed at Integration Board 14 Dec'17. CCG Executive Committee, CCG Finance Committee, CCG Quality, Innovation, Productivity and Prevention, Performance committee and CCG Integrated Governance Committee supported recommendation for joint commissioning structure 20 Dec'17. CCG Governing Body 10 Jan'18 confirmed the joint commissioning arrangements necessary to jointly commission integrated SEND services. CCG and Local Authority agree joint commissioning vision and arrangements April 2018.
|  | CCG Dionne Greenaway Senior Commissioning Manager Duncan Ambrose Assistant Director LA Sandra Bingham Head of Inclusion | D) Implement revised specifications in community paediatric therapies to address known gaps in CCG commissioned services | Target: Friday 01 Dec'17 Achieved: Friday 15 Dec'17 | Done | Specifications developed to cover all CCG registered children, 31 Mar'17. Timetable for implementation agreed with LNW, 17 May'17. Brent CCG and Brent Council agreed process to finalise specifications 13 Jul'17. Scope of contracts jointly reviewed 14 Aug'17. Confirmed CCG commissioned services for health-related SLT (acute dysphagia, stammering, voice problems, and significant hearing loss) accessible to CCG registered children, 14 Aug'17. Confirm alignment of special school services, 12 Oct'17. Ealing CCG on behalf of Brent CCG served notice to decommission LNW services 15 Dec '17. Clarificaton provided by Brent CCG to LNW that the prior approval process is available for extra-contractual health SLT cases outside EHCP, 15 Dec'17.
|  | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion | E) Jointly commission integrated paediatric therapy services (SLT, OT, PT) and specialist nursing services. Ensure services accessible for young people with complex SEND 0-25 including the most vulnerable groups, and those in alternative educational settings (e.g. LAC/ PRU/ YOS/ Home educated), in particular speech and language therapy. | Target: Monday 02 Apr'18 | Done | CCG and LNW agreed timetable for contract variation for paediatric therapies, addressing known gaps in SLT provision, 15 May'17. Map of existing SEND pathways in CCG and LA contracts completed 15 Sep'17. CCG and LNW confirm revised service specifications to cover all CCG GP registered children for SLT irrespective of education setting, 20 Sep'17. CCG write to LNW with strategic commissioning intentions, 29 Sep'17. Council for Disabled Children facilitated workshop for commissioners and providers to review pathways, statutory duties, and develop options 29 Sep'17. Targeted engagement with service users, schools, and HealthWatch to explore different options. Feedback shared at Health Partners Forum 18 Oct'17. Workshop with Council for Disabled Children to clarify existing resource and estimate future resource requirements 14 Dec'17. EY options appraisal on preferred joint commisisoning structure option 14 Dec'17. Joint Brent Council and CCG contract monitoring commenced Jan'18. Variations to existing LA contracts agreed to include children attending the Local Authority's Pupil Referral Units having access to therapy services in the same way as if they attend a mainstream school Jan '18. Alternative education setting providers expected to commission therapy as required by EHC Plans as part of their contracts Jan '18. New jointly commissioned therapies aligned contracts start date 02 Apr'18.
WSoA3 100% done, 0% in progress, 0% not started | Address the lack of opportunity for therapists to respond to draft EHC plans before they are finalised | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion | A) Strengthened EHCP process to obtain more consistent health professional input to EHCPs and for drafts to be shared | Target: Friday 15 Sep'17 Achieved: Monday 27 Nov'17 | Done | Changes to EHCP process agreed with LNW, 22 Aug '17 Weekly monitoring of input to EHCPs and sharing of draft EHCPs through contract monitoring from Sep '17 CCG confirmed with health providers sign off and Quality Assurance process for draft EHCPs, 01 Nov '17 Multi-agency training programme on completion of EHCPs launched 27 Nov'17 with 45 partner staff attending. 97% self reported improved understanding of the EHCP process and SEND. Quarterly partnership case sample audits to evidence improvement Apr '18 and Jul '18. | 1 | 100 | 100 | Done
|  | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion | B) CCG and LA review assurance process for the delivery of paediatric therapy services | Target: Tuesday 31 Oct'17 Achieved: Thursday 14 Dec'17 | Done | DCO work plan includes quality assurance feedback to health providers, 27 Sep'17. Assurance process review commenced 31 Oct '17 with all health providers. Results informed workshop with Council for Disabled Children, 14 Dec'17. Monthly monitoring meetings with Paediatric OT lead ensuring delivery of therapy for children with EHCPs in schools. | 0 | 0 | 0 | In progress
|  | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion | C) Ensure all paediatric therapists who contribute EHC needs assessment information are sent copies of draft EHC Plans for comment | Target: Friday 01 Sep'17 Achieved: Friday 01 Sep'17 | Done | Standard Operating Procedure with LNW to contribute to EHCP agreed 02 Aug'17. Distribution process of EHCPs agreed with health providers. Refreshed training programme implemented 01 Sep'17 Sharing of draft EHCPs being confirmed through weekly contract monitoring. Audit 20 Dec'17 verified that the new agreed procedures are working effectively
WSoA4 80% done, 20% in progress, 0% not started | Ensure timely access to paediatric diagnostic and therapy services. | CCG Dionne Greenaway Senior Commissioning Manager Diane Jones Director of Quality and Safety LNW Dr John Hutchins Clinical Director Maria Luscombe Head of Paediatric Therapies | A) London North West NHS Healthcare Trust to improve access to the service by maintaining a focus on recruitment for audiology and occupational therapy capacity and developing robust contingency plans (including partnerships with other providers) if recruitment is unsuccessful by October 2017. | Target: Friday 20 Oct'17 Revised target: Monday 02 Apr'17 Further Revised target: 11 May '18 | Done | LNW locum audiovestibular physician recruited, 23 Jun'17. Interim cover used to address vacancies monitored in weekly contract monitoring with LNW, CCG, Council, from 08 Aug'17. 1 WTE OT vacancy remaining under CCG contract, all OTs in post under LA contract, 12 Dec'17 National shortage of paediatric audiologists escalated to NHS England, 22 Aug'17. Fourth attempt to recruit for vestibular physician vacancy, Aug-Oct'17 Vestibular physician recruitment unsuccessful, being re-advertised for fifth time, 17 Oct'17. CCG Director of Quality in liaision with HENWL about audiology workforce planning, 27 Oct'17. Cooperation with Hounslow audiology service, confirmed clinic in Brent, 05 Dec'17. Additional OT capacity deployed Jan '18 Additional audiology capacity deployed Jan '18 Vestibular physician recruited substantively Apr '18. NHSE confirmed new service arrangement and skill mix is meeting all quality and performance requirements May '18 | 0.8 | 80 | 80
|  | CCG Dionne Greenaway Senior Commissioning Manager Duncan Ambrose Assistant Director Dr Sarah Basham Vice Chair LNW Dr John Hutchins Clinical Director Maria Luscombe Head of Paediatric Therapies CNWL Jackie Shaw Service Director for CAMHS | B) Reduce waiting times to ensure assessments comply with NICE guidance, and begin within 3 months of referral for children with suspected autistic spectrum disorder, with completion within 6 months | Target: Friday 29 Dec'17 Revised target: Friday 02 Feb'18 Further Revised target date: 31 May’18. | In progress | LNW re-prioritised clinical work focusing on the 56 cases waiting over 6 months for completion of assessment, 22 Aug'17. Council confirmed ASD diagnosis not required for EHC plan, only to access BOAT service, 13 Sep'17. CCG, Council, and LNW confirmed functional benefit for ASD cases is available from SLT service, 13 Sep'17. Monthly LNW review of children waiting over 6 months for completion of assessment commenced 13 Sep'17. Multi-agency workshop to review clinical pathway supported new joint clinics, 13 Sep'17. Two additional ASD clinics in place, 06 Oct'17. Two additional ASD clinics introduced, 17 Oct'17. Business case development started for joint CNWL and LNW joint clinic, 05 Dec'17. CCG supported LNW proposal for GPs and psychiatrists to screen rather than refer all cases to paediatricians Dec '18. LNW provided trajectory update to CCG, 31 Dec'17. Brent CCG led Healthy London Partnership ASD support mapping completed. Reporting on services and priority gaps reported to CCG 29 Dec '17 and Children's Trust Joint Commissioning Group Apr '18. CNWL implemented 4 week delivery plan between Apr and May ’18. Shared CNWL /LNWHT action plan in place from June 18 with a shared proposed model to recruit additional clinician capacity, informed by feedback from community paediatricians as to the most effective model. Recruitment commenced with expressions of interest received. Further meeting planned with community paediatriciains to operationalise. | 0.2 | 20 | 20 | In progress
|  | CCG Dionne Greenaway Senior Commissioning Manager Duncan Ambrose Assistant Director Dr Sarah Basham Vice Chair LA Melanie Smith Director of Public Health LNW Dr John Hutchins Clinical Director Maria Luscombe Head of Paediatric Therapies | C) Reduce waiting times for audiology services to meet the 6 week diagnostic target, and the 18 week referral to treatment target (RTT) | Target: Friday 08 Dec'17 Achieved: Friday 02 Feb'18 | Done | LNW locum audiovestibular physician recruited, 23 Jun'17. Weekly teleconference to monitor waits, vacancies, and action plans, 08 Aug'17. CCG formally wrote to LNW CEO to accelerate actions, 14 Aug'17 National shortage of paediatric audiologists escalated to NHS England, 22 Aug'17. Exploring capacity in other teams and providers, 22 Aug'17. Escalated concerns to NHS England London Regional Lead for SEND, 22 Aug'17. Public Health confirm parents are asked about their child's hearing at the 2 year review, 25 Aug'17 LNW decision on 12 additional clinics to achieve 6 week target, 15 Sep'17. LNW community audiologist starts 15 Sep'17. LNW decision on potential increase in audiovestibular physician hours, 12 Oct'17. Reconfigure admin to free up more clinical time, 12 Oct'17. Confirmed no waits over 6weeks for hospital audiology, 31 Oct'17. Confirmed 93 waits over 6 weeks for community audiology, 05 Dec'17. Cooperation with Hounslow community audiology service, confirmed additional clinic in Brent, 05 Dec'17. Joint Audit with DCO in Jan'18 6 week target met from 02 Feb'18.
|  | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion | D) Brent Council and Brent CCG will ensure joint commissioning activities provide assurance from providers that vulnerable groups will be supported to access services from October 2017 | Target: Tuesday 31 Oct'17 Revised target: Monday 02 Apr'18 | Done | CCG summary of statutory duties for SLT commissioning in strategic plan draft presented at Children's Trust, 11 Jul'17. CCG summary of statutory duties for SLT commissioning in strategic plan agreed at CCG Exec, 14 Jul'17. CCG conducts initial assessments in PRU. PRU confirm buy-in of SLT 20 Jul '17. Young Offenders institutions SLT commissioning confirmed from NHS England 20 Jul'17. Confirmation that home educated children able to access CCG health care if Brent GP registered 4 Aug '17. LNW, CCG, LA weekly contract monitoring started, with a brief to ensure gaps in services were addressed 08 Aug'17. CCG confirms a 'prior approval' process to spot purchase therapies to address gaps in service 20 Aug '17. Brent Council and CCG agreed 'stage zero' process to scope services for potential joint commissioning of paediatric therapies Sep'17, including contract variations to ensure that vulnerable groups can access services. CCG, LA, and LNW meeting reviewed contract variations to resolve commissioning gaps, 11 Dec'17. Council for Disabled Children led multi-agency workshop on 2018/19 integrated specification to meet statutory duties of LA and CCG and address gaps in pathways, 14 Dec'17. Joint contract monitoring CCG, LA with LNW, commenced Jan'18 Equality Impact and Needs Assessment for re commissioning completed Jan'18 Contract timetable confirmed with LNW, 11 Jan'18. New integrated specifciation with LNW implemented from 01 Apr'18
|  | CCG Dionne Greenaway Senior Commissioning Manager LA Sandra Bingham Head of Inclusion LNW Dr John Hutchins Clinical Director Maria Luscombe Head of Paediatric Therapies | E) Reduce waiting times for occupational therapy (OT) services to meet the 18 week referral to treatment target (RTT) | Target: Friday 29 Dec'17 Revised target: Friday 02 Feb'18 Further Revised target date: 30 Apr’18. | Done | Weekly monitoring of waits, vacancies, and action plans, 08 Aug'17. CCG contract maternity leave and sickness cover. Agency staff interviews 16 Aug'17, appointments 30 Aug'17. CCG and LNW clarified costs for additional agency staff, 22 Aug'17. LA and LNW reviewed all children's EHCPs to determine staff capacity needed, 25 Aug'17. LNW confirmed trajectory for recovery of RTT compliance, 01 Sep'17. LA commissioned therapy staff for new school term, 04 Sep'17. OT recruitment difficulty escalated to NHS England London Region SEND lead for advice, 26 Sep'17. LNW unable to attract staff with internal rotation option advised by NHS England, 17 Oct'17. CCG requested quantification of staffing resource required to meet targets, 03 Oct'17. CCG in discussion with other providers for additional capacity, 17 Oct'17. LNW developing business case to quantify resource needed, 31 Oct'17. CCG-led RTT recovery meeting, LNW business case for £40k not supported by Trust, 09 Nov'17. CCG supported £40k non-recurrently without prejudice, 14 Dec'17. Joint audit led by DCO in Jan'18. Findings informed service improvement plans through contract moitoring Feb '18 Achieved RTT compliance 30 April '18
WSoA5 100% done, 0% in progress, 0% not started | Improve the opportunities for parental involvement when commissioning and designing services | CCG Michelle Johnson Head of Engagement LA Sandra Bingham Head of Inclusion Brent Parent/Carer Forum Carol Foyle | A) Strengthen Parent/Carer Forum involvement in commissioning | Target: Wednesday 14 Sep'17 Achieved: Monday 20 Nov'17 | Done | Brent Council and CCG supported relaunched Parent/Carer Forum Aug '17. Parent/Carer Forum 14 Sep'17 coproduced desired ambitions for service delivery set out in the WSoA. Targeted joint engagement event dates sent for families using SEND services, working with Parent/Carer Forum 08 Sep'17. CCG engagement workshops for SEND parents 21 Sep'17, consulted on access to local health services. Parent/Carer Forum receiving updates on progress of WSoA from Nov '17. Parent/Carer Forum 23 Nov'17 consulted on short breaks and local offer commissioning intentions. Update on WSoA and joint commissioning of therapy services at Parent/Carer Forum 18 Jan'18 | 1 | 100 | 100 | Done
|  | CCG Dionne Greenaway Senior Commissioning Manager Michelle Johnson Head of Engagement LA Nigel Chapman Operational Director (Chair Inclusion Strategic Board) HealthWatch Ian Niven Head of HealthWatch Brent Brent Parent/Carer Forum Carol Foyle | B) Fully engage parents and carers in the workstream of the inclusion strategic board to develop and plan services through co-production | Target: Friday 10 Nov'17 Revised target: Friday 02 Apr'18 | Done | Standing forum for CAMHS established, Sep'17. CCG and HealthWatch agreed to coordinate engagement, including the Parent/Carer forum, 22 Sep'17. Targeted engagement dates agreed with schools, 29 Sep'17. Strategic inclusion work streams identify parent/carer and young people representatives, 29 Sep'17. Feedback on involvement of parent/carers to public 'You said, we did' at Health Partners Forum, 18 Oct'17. Parent/Carer involvement in service reviews commenced through work streams Sep '17 Parent/Carer involvement in revision and implementation of refreshed service specifications through joint commissioning workstream 27 Sep'17, 31 Oct'17, 21 Nov'17. Parent/carer coproduction of service delivery principles for specifications (access, integration, responsiveness, person centred). "Journey of Life" day 22 March '18 co produced with parent/carers on available services and support - posiitve parent/carer and practitioner feedback Parent/Carer designed and led service questionnaire distributed to all Parent/Carers April '18 to evaluate impact of service review and improvement actions Parent/Carer Forum received update on service improvements made as a result of coproduction Mar'18 Parent/Carer Forum consulted on commissioning priorities for 2018/19 Mar '18 and views informed commissioning plan Parent/Carers involved in contract monitoring through the joint commissioning workstream from 2 Apr'18 Journey of Life event 22 March '18 led by Brent Parent/Carer Forum provided opportunities for parent/carers to contribute to service development as well as learn more about services available. Parent/carer survey results informed SEND strategy implementation plan June '18 | 0 | 0 | 0 | In progress