## Actions
Brent Local Plan Examination 2020 - Actions that came out of the hearings sessions
Action locator | Post Hearing Action (PHA) document REF | Matter | Action | Document or mod?
1 | PHA_01 | Matter 1- Legal & Procedural Requirements | Obtain written response from Natural England with regards to the HRA. | Natural England reg 19 HRA response
2 | N/A | Matter 1- Legal & Procedural Requirements | Appendix 1 of the plan - Review the table on page 388 (possibly delete) | MOD
3 | PHA_02 | Matter 1- Legal & Procedural Requirements | Amend SCI and LDS to ensure consultation changes due to COVID19 are addressed when moving forward with the next stages of the Plan’s adoption/consultation on proposed modifications. | Covid SCI
4 | PHA_03 | Matter 2 - Vision, strategy & objectives | Supply better quality copy of key diagram including more detail e.g. numbers for growth areas, balancing need for additional information with need for clarity. | Key diagram
5 | PHA_04 | Matter 2 - Vision, strategy & objectives | Revisit Appendix 6 strategic and non- strategic policies. Clarify/ justify which are strategic policies taking account of the NPPF and NPPG definitions. | STRATEGIC and NON-S POLICIES
6 | N/A | Matter 2 - Vision, strategy & objectives | Produce and include contents page for the final version of the Plan. In the interim email contents page to the Inspectors | N/A
7 | N/A | Matter 2 - Vision, strategy & objectives | Council to consider the requests for mods from STRA which we will receive in writing. | MOD
8 | N/A | Matter 3 - Flood risk | Council to clarify with Environment Agency the modifications required to the Plan to adequately reference consideration of flooding issues identified in the SFRA Level 2. | MOD
9 | N/A | Matter 3 - Flood risk | Amend mod MiM202 from Core_04a to read ‘insert below paragraph after 6.7.35’ once all modifications consolidated. It should also reference MiM102 not 202. | MOD
10 | N/A | Matter 3 - Flood risk | Review paragraph 6.7.36 to identify whether or not it comprehensively supports the policy. | MOD
11 | N/A | Matter 3 - Flood risk | Produce Policy BSUI3 including the modifications- the full revised policy. | MOD
12 | N/A | Matter 3 - Flood risk | Review MM295 with regards to permissions in functional floodplain being ‘refused’– is this in line with NPPF as stated? | MOD
13 | N/A | Matter 3 - Flood risk | Consolidate Core_04a and b into one document, titled Core_04c. | Consolidated with new mods in modifications folder
14 | N/A | Matter 3 - Flood risk | Expedite agreement with GLA on staples corner sticking point prior to discussions on matter 6. | N/A
15 | PHA_05 | Matter 4 - Strategic Transport, Infrastructure and Delivery | Obtain update on the progress of the car club management plan | TfL car club strategy
15 | PHA_06 | Matter 4 - Strategic Transport, Infrastructure and Delivery | Obtain update on the progress of the car club management plan | parking-policy-2020-v5
16 | PHA_07 | Matter 4 - Strategic Transport, Infrastructure and Delivery | Obtain update on bespoke transport strategy for Wembley. | Western Corridor Study
16 | PHA_08 | Matter 4 - Strategic Transport, Infrastructure and Delivery | Obtain update on bespoke transport strategy for Wembley. | Medium Term Plan 2018 - 2022
17 | N/A | Matter 4 - Strategic Transport, Infrastructure and Delivery | Include new criteria in BT1 to reference supporting bus network | MOD
18 | N/A | Matter 4 - Strategic Transport, Infrastructure and Delivery | Revise first paragraph of BT2 and paragraph 6.8.17 with regards to use of car-free development conditions, to ensure it accords with London Plan policy T6- Car Parking. | MOD
19 | PHA_09 | Matter 4 - Strategic Transport, Infrastructure and Delivery | Infrastructure Provision: Further piece of work required: Look in more detail at phase 2 and phase 3 (to best of our abilities) to find out in particular what healthcare and education facilities (Primary, secondary and Special Education Needs categories to be covered) will be produced in the later stages of the plan. Refer providers back to para 20 of the framework if they state they don’t plan as far forward as us. | Brent long term infrastructure needs
19 | PHA_10 | Matter 4 - Strategic Transport, Infrastructure and Delivery | Infrastructure Provision: Further piece of work required: Look in more detail at phase 2 and phase 3 (to best of our abilities) to find out in particular what healthcare and education facilities (Primary, secondary and Special Education Needs categories to be covered) will be produced in the later stages of the plan. Refer providers back to para 20 of the framework if they state they don’t plan as far forward as us. | Appendix A: phase 1 infrastructure projects
20 | N/A | Matter 4 - Strategic Transport, Infrastructure and Delivery | Email the correct IDP statement to Inspectors | MOD
21 | N/A | Matter 4 - Strategic Transport, Infrastructure and Delivery | Send details of stacked warehouse / commercial development in Park Royal | MOD
22 | N/A | Matter 4 - Strategic Transport, Infrastructure and Delivery | Note that Proposed MM256 (p44 – ‘Core_04’ [Feb 2020 Schedule]) relates to Policy BT1 and not BT2 as stated in the Schedule. Council to amend accordingly. | MOD
23 | N/A | Matter 5 - Requirement & Strategy | BH1 - Delete words ‘and beyond’ from first sentence. Remove references to planning beyond plan period from policy commentary paragraphs. | MOD
24 | PHA_11 | Matter 5 - Requirement & Strategy | Write a short report to state a housing requirement for the Neighbourhood Areas which expresses compliance with NPPF paragraph 65. It was mentioned to express this as a minimum. | Neighbourhood forum area housing figure report final
25 | N/A | Matter 5 - Requirement & Strategy | Suggest where in the plan we can add Brent's priority areas for growth and where these are being focused at. Possibly in our good growth section of the Plan, and in ‘Place’ sections, and BH1 and reflect better in the Key diagram. | MOD
26 | PHA_12 | Matter 5 - Requirement & Strategy | Review the method of presentation / identification of Intensification Corridors, in terms of boundaries. See action under matter 7 below. | Intensification Corridors Background Report
27 | N/A | Matter 5 - Requirement & Strategy | Appendix 3 – fix the formatting as it repeats the ‘year’ category and make it clearer (i.e. years division, the buffer, year target and refer to NPPF/PPG in terms of formatting requirement). | MOD
28 | N/A | Matter 5 - Requirement & Strategy | Also update it to the recent trajectory. It needs to be clear in the plan as to how we have reached these figures. | MOD
29 | PHA_13 | Matter 5 - Requirement & Strategy | Prepare a note on the small site windfall requirement/ assumptions: cover what we did, how we did it, how it is applied – how they have been translated into the housing trajectory. Rename as small sites and not windfall. | Small sites Delivery Assumptions in the Brent Local Plan Dec 20
30 | N/A | Matter 5 - Requirement & Strategy | Remove student accommodation element from BCSA6 (as likely completed) | MOD
31 | N/A | Matter 5 - Requirement & Strategy | Northwick Park Growth Area delivery on trajectory – push back first completions by at least one year. | MOD
32 | N/A | Matter 5 - Requirement & Strategy | Policy BH3 – revisit criteria to address viability | MOD
33 | N/A | Matter 5 - Requirement & Strategy | Policy BH4 – update to reflect main mods. | MOD
34 | N/A | Matter 5 - Requirement & Strategy | To make reference to the most up to date TfL PTAL map. | MOD
35 | N/A | Matter 5 - Requirement & Strategy | Look into potential of the policies map to have a layer on PTAL ratings which is possibly linked to real-time update. | See progress update
36 | PHA_14 | Matter 5 - Housing- affordable housing and housing mix | Clarify Borough Plan affordable housing target of 5000 homes in 5 years in the trajectory. | Affordable housing delivery housing trajectory GROSS
36 | PHA_15 | Matter 5 - Housing- affordable housing and housing mix | Clarify Borough Plan affordable housing target of 5000 homes in 5 years in the trajectory. | Affordable housing delivery housing trajectory NET
37 | N/A | Matter 5 - Housing- affordable housing and housing mix | Within BH5, highlight connection with London Plan H4 on commuted sums in lieu of affordable housing- adjust words to ensure clarity and reference Mayor’s Affordable Housing and Viability SPD and our forthcoming Planning Obligations SPD. | MOD
38 | N/A | Matter 5 - Housing- affordable housing and housing mix | Make sure all London Plan policy/paragraph references are correct taking account of Intend to Publish version. | MOD
39 | N/A | Matter 5 - Housing- affordable housing and housing mix | Double check point on emphasis on family sized accommodation- is this re emphasis throughout the wider plan – Page 30 c) – possibly remove ‘recognising that Brent’s suburban context provides opportunities for houses as well as flats’ as it is not clear where this has been emphasised elsewhere? | MOD
40 | N/A | Matter 5 - Housing- affordable housing and housing mix | Removal of reference to family accommodation in BSWSA5 and also in the wider Plan – particularly where there may be a ‘double emphasis’. | MOD
41 | N/A | Matter 5 - Housing- affordable housing and housing mix | 6.2.9 & 6.2.54 – check for consistency in reference to % need for 3+ bed dwellings as a proportion of all dwellings - inconsistency arises as a result in referencing outputs of two different SHMAs. | MOD
42 | N/A | Matter 5 - Housing- affordable housing and housing mix | Amend reference to education in policy BH7 to 'purpose built' student accommodation in criterion d). | MOD
43 | PHA_16 | Matter 5 - Housing- affordable housing and housing mix | Justification on threshold levels for policy BH7 4 of 11 for HMOs and how it will work in practice in terms of assessment/ impacts where there might already be a concentration but not within the 5 adjacent properties either side. | Houses in Multiple Occupation Policy BH7 Note
44 | N/A | Matter 5 - Housing- affordable housing and housing mix | Amend policy BH8 to assert a minimum of 10% of units from the following to be older persons housing | MOD
45 | N/A | Matter 5 - Housing- affordable housing and housing mix | Include guidance on council’s approach in justification to policy BH8 on flexibility of delivery across the growth areas. | MOD
46 | N/A | Matter 5 - Housing- affordable housing and housing mix | Review policy BH9 in light of LP policy equivalent, part f, and the need to retain the Lynton Close site considering current discussions as to its potential relocation/ expansion. | MOD
47 | N/A | Matter 5 - Housing- affordable housing and housing mix | Look at the terminology of G&T within the Plan and consistency with London Plan. | MOD
48 | N/A | Matter 5 - Housing- affordable housing and housing mix | Include MM (already proposed) for clarity around family private amenity space in policy BH13. | MOD
49 | PHA_17 | Matter 6- Economy & Town Centres | The Council is required to work with the OPDC with the OPDC leading, on a Statement of Common Ground, possibly involving Ealing/GLA following completion of the OPDC industrial land studies, to establish what quantum of industrial space will be attributed to Brent Council. | OPDC statement
50 | N/A | Matter 6- Economy & Town Centres | Clarify whether 6,100sqm floorspace in the retail study is a commitment to the South West place as a whole and what the footnote refers to. – Inspectors subsequently updated for Central and South West Places policies taking account of retail study outputs. Is 2,100 sqm comparison and 4,800 convenience to apply in total across both Places. | MOD
51 | N/A | Matter 6- Economy & Town Centres | Insert text ‘Unviable secondary frontages as shown on the policies map’ in Policy BE4 | MOD
52 | PHA_18 | Matter 6- Economy & Town Centres | Edit figure 34 to align the colouring of the town centres on the map with the key... (as set out in the modification MiM128) | Figure 34 town centre hierarchy
53 | N/A | Matter 6- Economy & Town Centres | Amend Policy BE4 to support additional public houses outside the defined frontages | MOD
54 | PHA_19 | Matter 6- Economy & Town Centres | Policy BE5: Look into more up-to-date evidence and reflect that in the map for shisha cafes. Can refer to Barnet’s evidence base but needs to be more up-to-date than 2012. | Shisha cafe locations map nov 2020
55 | N/A | Matter 6- Economy & Town Centres | Policy BE5: Make a note on which town centre manager we got part (e) information from and why the threshold of that policy needs to be amended. | MOD
56 | N/A | Matter 7 - Design, Heritage and Culture | Tall Buildings - appropriate building heights for each TBZ as identified in the Tall Building Strategy needs clarification or additional wording within the Plan/on Proposals Map. | MOD
57 | PHA_20 | Matter 7 - Design, Heritage and Culture | Find out when Barnet’s next consultation stage is for their draft Local Plan. The view from Golder’s Hill to Harrow on the Hill needs to be agreed with Barnet / get a statement from Barnet that this is the correct view Needs to be a map accompanied by a statement saying we have both agreed it. | Barnet views report statement
58 | N/A | Matter 7 - Design, Heritage and Culture | Remove the core and pinnacles on the policies map. | MOD
59 | N/A | Matter 7 - Design, Heritage and Culture | BD2: Look at potential for re-wording once the places sections are completed. | MOD
60 | N/A | Matter 7 - Design, Heritage and Culture | Inspector Masters to clarify the policies map and building heights issue as required by the London Plan Tall buildings policy. | MOD
61 | PHA_12 | Matter 7 - Design, Heritage and Culture | The council to undertake a piece of work in the context of 6.1.17 to explain what an intensification corridor is. Revisit the ones proposed using that as our criteria. Provide something to support their existence. By default, an intensification corridor cannot be anindividual site in a corridor. Look at the output as to how that is translated into the policies map. Should set out the methodology used to assess those. Exercise undertaken and outputs and conclusions including an assessment of how they appear and what might need to change based on that methodology and exercise undertaken. Consider consulting with others before we undertake that work. | Intensification Corridors Background Report
62 | N/A | Matter 7 - Design, Heritage and Culture | 6.5.24 – (MiM141) remove “the presumption will be” sentence. | MOD
63 | N/A | Matter 7 - Design, Heritage and Culture | BHC1 Par C: Amend to say “substantial harm…. loss or harm of a designated heritage asset must only be in exceptional circumstances” or similar to strengthen that policy. | MOD
64 | PHA_21 | Matter 8- Social, Green and Sustainable Infrastructure | Enquire with cemeteries staff to obtain update on the capacity of burial sites within the borough to 2041. | cemeteries capacity statement
65 | N/A | Matter 8- Social, Green and Sustainable Infrastructure | For session 9: clarify method of expressing requirement for 'open space' within growth areas, with references to the 8sqm of public open space per person required. | MOD
66 | N/A | Matter 8- Social, Green and Sustainable Infrastructure | In paragraph 6.6.31, add reference to consultation with CRT regarding Welsh Harp, to last sentence. | MOD
67 | N/A | Matter 8- Social, Green and Sustainable Infrastructure | Define more clearly in Policy BGI2 and in paragraph 6.6.39, the requirements for ‘equivalent canopy cover’ – discussion was based on 4 trees within 25 years per replacement for one larger canopy tree. | MOD
68 | N/A | Matter 8- Social, Green and Sustainable Infrastructure | Define whether BSUI4 and BD3 are ‘Strategic Policies’ for Appendix 6. | MOD
69 | N/A | Matter 8- Social, Green and Sustainable Infrastructure | The three documents referred to in the footnotes on page 2 of the MIQ8 response need to be sent to Andrea Copsey. | MOD
70 | N/A | Matter 9 - General actions across all places | Decide on a standardised approach to policies for Growth Areas, rather than different approach for new versus old as currently exists. | MOD
71 | N/A | Matter 9 - General actions across all places | Consider need for ‘Key Site Allocations’ within each Place chapter | MOD
72 | N/A | Matter 9 - General actions across all places | Decide on a standardised approach to how we express requirement for masterplanning across all allocations. | MOD
73 | N/A | Matter 9 - General actions across all places | Strike out references to Brent being a “provide capacity” borough | MOD
74 | N/A | Matter 9 - General actions across all places | A lot of the site allocation planning considerations are very narrative and written like an officer report rather than a policy – remove unnecessary text throughout the Plan in the allocations and focus on specific outputs/issues to be addressed. | MOD
75 | N/A | Matter 9 - General actions across all places | Remove references to Wembley Area Action Plan | MOD
76 | N/A | Matter 9 - General actions across all places | Cross check throughout the Plan: references student accommodation – should be no differentiation between this and conventional residential throughout the Plan. | MOD
77 | N/A | Matter 9 - Central Place | Policy BP1 a): Amend to reference the identified tall building zone rather than masterplan area as a whole. | MOD
78 | N/A | Matter 9 - Central Place | Cross reference to policy BE1 in BP1 (l) | MOD
79 | N/A | Matter 9 - Central Place | Policy BP1 and supporting paragraphs in the Place: Think about the clarity of the Wembley Masterplan area vs the Wembley Growth Area – is it clear to readers? | MOD
80 | N/A | Matter 9 - Central Place | Consider taking out the “Key Site Allocations” on page 50 | MOD
81 | N/A | Matter 9 - Central Place | “Other Planning Guidance” on page 50 – might be better referenced in the site allocations (if not already) | MOD
82 | N/A | Matter 9 - Central Place | Delete the sentence “(that also crosses into the South West place)” that was included in MM297. | MOD
83 | N/A | Matter 9 - Central Place | 5.1.19 (page 46). Amend to reflect tall building discussions yesterday. “further guidance on the tall buildings…..” this is referencing we currently have core and pinnacle and tiered designations, which is what the Inspectors consider we should move away from. What we have said in BP1a adequately covers the context for tall buildings. | MOD
84 | N/A | Matter 9 - Central Place | BP1l) Cross reference back to BE1 | MOD
85 | N/A | Matter 9 - Central Place | 5.1.30: take out paragraph “If however there has been no…..” | MOD
86 | N/A | Matter 9 - Central Place | BP1: retail floorspace amalgamate central and south west to 2,100 sqm comparison and 4,300 sqm convenience with a footnote that the total can be delivered across Central and South West"- Replicate in BP7. | MOD
87 | N/A | Matter 9 - Central Place | Re Wembley Opportunity Area: “the site is located within the Wembley opportunity area” is sufficient – we don’t need to superimpose London Plan allocations on our policies map (page 71). Acknowledge in the supporting text, as we have done. | MOD
88 | N/A | Matter 9 - Central Place | 5.1.33: York House - make sure we have referenced the nursery and primary element, for consistency | MOD
89 | N/A | Matter 9 - Central Place | BCSA1: Need to correlate the figures with the trajectory | MOD
90 | N/A | Matter 9 - Central Place | BCSA2: knock out reference to Wembley masterplan – amend justification – amend throughout the plan | MOD
91 | N/A | Matter 9 - Central Place | BCSA2: should be zone 2 and 3a. | MOD
92 | N/A | Matter 9 - Central Place | BCSA4: allocated use “employment and residential” - no student accommodation and hotel use (to be struck out) | MOD
93 | N/A | Matter 9 - Central Place | BCSA4: Remove most of the risks, as an application has been put in. Change to “none”. | MOD
94 | N/A | Matter 9 - Central Place | BCSA4: Public access to brook and Thames water reference needs to go under infrastructure requirements. | MOD
95 | N/A | Matter 9 - Central Place | Move the waste element of BCSA4 to BCSA9 which has the remainder of the waste site in single ownership – redo the red line for BCSA4 and BCSA9. Amend capacity on site to reflect this as set out in the trajectory. | MOD
96 | N/A | Matter 9 - Central Place | BCSCA4: Reconsider whether a masterplanning approach would be required (should the application fall through??) something to consider – probably need to strike out. | MOD
97 | N/A | Matter 9 - Central Place | BCSA5: Delete the old use classes. | MOD
98 | N/A | Matter 9 - Central Place | BCSA6: Amend the site area so student accommodation is removed from the allocation. | MOD
99 | N/A | Matter 9 - Central Place | Need to amend trajectory to reflect removal of completed / under construction sites (BCSA6) | MOD
100 | N/A | Matter 9 - Central Place | MM42 – take out | MOD
101 | N/A | Matter 9 - Central Place | BCSA7: separate into two sites | MOD
102 | N/A | Matter 9 - Central Place | BCSA7: delivery needs to be amended in line with the trajectory. | MOD
103 | N/A | Matter 9 - Central Place | BCSA7: need to reflect on whether what we’ve said in planning considerations reflects what we’ve said in MM32. | MOD
104 | N/A | Matter 9 - Central Place | BCSA8: Remove reference to the WAAP tall buildings and identify the site being within the Tall Buildings Zone. | MOD
105 | N/A | Matter 9 - Central Place | BCSA9: Will need to insert what’s on the trajectory. | MOD
106 | N/A | Matter 9 - Central Place | BCSA9: Strike out reference to 1200 | MOD
107 | N/A | Matter 9 - Central Place | BCSA9: SIL – no longer relevant. | MOD
108 | N/A | Matter 9 - Central Place | BCSA9: Add some text to planning considerations regarding these replacement uses. | MOD
109 | N/A | Matter 9 - Central Place | BCSA9: Replace reference to a noise assessment with agent of change principle | MOD
110 | N/A | Matter 9 - Central Place | BCSA9: Push back the access storage element so as not to be within the 5 year supply. Add the waste facility issue as a planning consideration. | MOD
111 | N/A | Matter 9 - Central Place | BCSA10: Ensure allocation reference to both nursery and primary if is both and number of forms of entry. (Same details currently set out in planning history). | MOD
112 | N/A | Matter 9 - Central Place | Do a sense check on Figure 11 (page 78) – as references may not make sense to people reading it. Could re-define as existing commitments. | MOD
113 | N/A | Matter 9- East | Include reference to Cricklewood LSIS being partly in the East Place, in para 5.2.8 | MOD
114 | N/A | Matter 9- East | BP2 d) Add a reference to policy BD2 | MOD
115 | N/A | Matter 9- East | Add additional point q) under ‘Employment and skills’ in BP2 to capture a varied mix of employment uses. | MOD
116 | N/A | Matter 9- East | Key site allocations – amend to Neasden and Staples Corner | MOD
117 | N/A | Matter 9- East | Remove other Policy Guidance contents. | MOD
118 | N/A | Matter 9- East | BEGA1: Revise red line to amalgamate site allocation into one area | MOD
119 | N/A | Matter 9- East | BEGA1: Update planning considerations to reflect status of masterplan (see MM61) | MOD
120 | N/A | Matter 9- East | BEGA1: Update policy capacity to accurately reflects trajectory | MOD
121 | N/A | Matter 9- East | BP2: Add ‘Challenges and Opportunities’ for East Place and add lines to reflect rep on cited poor quality frontage. | MOD
122 | N/A | Matter 9- East | BEGA2: Highlight the intention to work towards masterplan between Brent, Barnet and GLA within the Planning considerations section. | MOD
123 | N/A | Matter 9- East | BEGA2: Edit planning considerations section, and delineate better between ‘planning considerations’ and ‘design considerations’. | MOD
124 | N/A | Matter 9- East | BESE3: Update indicative homes to reflect recent application. | MOD
125 | N/A | Matter 9 - North area | 5.3.29: Amend name ‘Queensbury LSIS’ to reflect correct LSIS name- ‘Lowther Road’ | MOD
126 | N/A | Matter 9 - North area | BNGA1: Reflect allocation change (MM299) in BP3 into BNGA1 | MOD
127 | N/A | Matter 9 - North area | BNSA1: Update capacity to match trajectory | MOD
128 | N/A | Matter 9 - North area | BNSA1: Add line under ‘planning considerations to reflect fact that site is not entirely within LSIS and to explain existing uses" | MOD
129 | N/A | Matter 9 - North area | BNSA1: MM99: Examine ‘transitioning uses’ wording to explain better what this means | MOD
130 | N/A | Matter 9 - North area | BNSA1: Revise requirement for masterplan to reflect extant permissions | MOD
131 | N/A | Matter 9 - North area | BNSA3: Rename the site to reflect the correct name as per LSIS name | MOD
132 | N/A | Matter 9 - North area | BNSA3: Update ‘timeframe for delivery’ to reflect trajectory | MOD
133 | N/A | Matter 9 - North area | BNSA3: Revise wording requirement for masterplan to reflect extant permissions | MOD
134 | N/A | Matter 9 - North area | BNSA4: Update indicative capacity to reflect trajectory | MOD
135 | N/A | Matter 9 - North area | BNSA4: Revise order of words/ emphasis on 'allocated use' | MOD
136 | N/A | Matter 9 - North West area | BP4: Remove reference to Northwick Park Master Plan/ Supplementary Planning Document/ Area Action Plan (forthcoming) | MOD
137 | N/A | Matter 9 - North West area | BNWGA1: Update delivery under 0-5 years to reflect trajectory and revisit overall quantum of development to reflect assumptions in outline planning application – as also discussed in the housing trajectory session. | MOD
138 | N/A | Matter 9 - North West area | BNWGA1: Add reference to local views within planning considerations | MOD
139 | N/A | Matter 9 - South area | SIL boundaries consistent with what they discuss today | MOD
140 | N/A | Matter 9 - South area | insert opportunities and constraints that was missed out of the document by the printers | MOD
141 | N/A | Matter 9 - South area | Check rationale, implementation, consistency and spatial distribution of creative quarters – through all places as they relate to those specified within paragraph 6.4.25. | MOD
142 | N/A | Matter 9 - South area | Check reference to community facilities across the allocations to make it consistent | MOD
143 | N/A | Matter 9 - South area | Clarify first bullet in BSGA1 as follows: ‘A new space to serve as an employment, community and health hub’ | MOD
144 | N/A | Matter 9 - South area | For consistency cross reference market policy (BE8) within planning considerations of BSSA3. | MOD
145 | N/A | Matter 9 - South area | Rework planning considerations and design principles of BSSA6 as no longer local employment site and BE3 does not apply; and in relation to new flooding information | MOD
146 | N/A | Matter 9 - South East area | Amend wording of creative clusters to make consistent throughout the plan (in reference to opportunities table). | MOD
147 | N/A | Matter 9 - South East area | Amend last bullet in opportunities column as it relates to Kensal canal development to identify what the opportunity is. | MOD
148 | N/A | Matter 9 - South East area | Specify that other policy guidance ‘design guides’ are ‘conservation area design guides’. | MOD
149 | N/A | Matter 9 - South East area | Map required for BSESA21 | MOD
150 | N/A | Matter 9 - South East area | Clarify market use in BSESA21- relate to markets policy | MOD
151 | N/A | Matter 9 - South East area | Update the key site allocations to reflect the names that are in the site allocations policies | MOD
152 | N/A | Matter 9 - South East area | BSEGA1 – put in supporting text which explains indicative capacity as proposed for a number of sites (SK regeneration sites) re. loss of existing housing as a result of regeneration. | MOD
153 | N/A | Matter 9 - South East area | Insert in BSESA9 allocation reference in relation to reprovision of green space over to BSESA8. | MOD
154 | N/A | Matter 9 - South East area | Amend timeframes for delivery within BSESA13 in accordance with housing trajectory | MOD
155 | N/A | Matter 9 - South East area | Amend timeframes for delivery within BSESA14 in accordance with housing trajectory | MOD
156 | N/A | Matter 9 - South East area | BSESA16: clarity on intentions for upgrading/ reprovision of community use on/off site. | MOD
157 | N/A | Matter 9 - South East area | BSESA18: should reflect BE3, not BE2 intensification. | MOD
158 | N/A | Matter 9 - South East area | BSESA20: clarify name, add map, reference BE8 for markets | MOD
159 | N/A | Matter 9 - South East area | BSESA21: add map, amend description/ allocation name/ justification to reflect new garage use. Increase in employment use will be required if still has employment function. | MOD
160 | N/A | Matter 9 - South West area | Achieve consistency to the naming of the Northfields site both on map and on page 246. | MOD
161 | N/A | Matter 9 - South West area | BSWSA3: Adjust delivery / timeframes to match trajectory. | MOD
162 | N/A | Matter 9 - South West area | BSWSA4: Adjust delivery / timeframes to match trajectory. | MOD
163 | N/A | Matter 9 - South West area | BSWSA4: Adjust references to tall buildings to reflect changes to tall buildings terminology | MOD
164 | N/A | Matter 9 - South West area | BSWSA5: Adjust delivery / timeframes to match trajectory. | MOD
165 | N/A | Matter 9 - South West area | BSWSA3, 4, 5, and 6: Align wordings with regards for requirement for cycle and pedestrian links between the sites and along canal (same place in allocation text and similar wordings) | MOD
166 | N/A | Matter 9 - South West area | BSWSA5: Remove reference to ‘provide capacity borough’ with refs to industrial space and refer to policy BE2 or BE3 as appropriate. | MOD
167 | N/A | Matter 9 - South West area | BSWSA5: Remove reference to family units within design principles design principles to reflect consideration of planning permission | MOD
168 | N/A | Matter 9 - South West area | BSWSA6: Adjust delivery / timeframes to match trajectory | MOD
169 | N/A | Matter 9 - South West area | BSWSA6: Remove reference to Alperton Masterplan | MOD
170 | N/A | Matter 9 - South West area | BSWSA6: Remove reference to ‘provide capacity borough’ with refs to industrial space. | MOD
171 | N/A | Matter 9 - South West area | BSWSA7: Adjust reference to ‘existing industrial use’ to reflect the ongoing development and remove reference to Park Royal SIL – make same as BE2 reference set out in SoCG with GLA. | MOD
172 | N/A | Matter 9 - South West area | BSWSA7: Remove reference to ‘provide capacity borough’ with refs to industrial space and refer to policy BE2 or BE3 as appropriate. | MOD
173 | N/A | Matter 9 - South West area | BSWSA7: Revisit planning considerations and design principles inc. whether there is requirement for masterplan and in light of current development and ongoing requirement to retain element of industrial. | MOD
174 | N/A | Matter 9 - South West area | BSWSA7: Revisit risks and references to ‘market appetite’. | MOD
175 | N/A | Matter 9 - South West area | BSWSA8: Adjust delivery / timeframes to match trajectory | MOD
176 | N/A | Matter 9 - South West area | BSWSA8: Add Tall Buildings Zone to planning considerations | MOD
177 | N/A | Matter 9 - South West area | BSWSA8: Remove reference to provide capacity borough and refer to BE3 as appropriate. | MOD
178 | N/A | Matter 9 - South West area | BSWSA9: Remove reference to WAAP and adjust the planning considerations to reflect inclusion in TBZ and wordings refs ‘sensitivity to (very?) tall buildings. | MOD
179 | N/A | Matter 9 - South West area | BSWSA10: Adjust timeframe for delivery / remove reference to provide capacity borough | MOD
180 | N/A | Matter 10 - Delivery & Monitoring | Insert in para 7.1.20 monitoring arrangements for infrastructure in relation to AMR, Infrastructure Funding Statement, and governance arrangements. | MOD
181 | N/A | Matter 10 - Delivery & Monitoring | Clarify what action would be taken if the targets were not being met – i.e. plan monitor, manage etc. to be included in para 7.1.22 | MOD
182 | N/A | Matter 10 - Delivery & Monitoring | Amend reference to BD1 tall building zones policy to BD2. | MOD
183 | N/A | Matter 10 - Delivery & Monitoring | Amend reference to basements policy from BD2 to BD3. | MOD
184 | N/A | Matter 10 - Delivery & Monitoring | New measure for 100% London Living Rent in relation to BH5 and BtR schemes | MOD
185 | N/A | Matter 10 - Delivery & Monitoring | Amend reference from affordable rent to ‘London’ affordable rent and remove reference to below LHA allowances | MOD
186 | N/A | Matter 10 - Delivery & Monitoring | Amend proposed modification ‘no target’ to ‘no specified target’ throughout. | MOD
187 | N/A | Matter 10 - Delivery & Monitoring | Review gypsy and traveller target when London Plan definition confirmed | MOD
188 | N/A | Matter 10 - Delivery & Monitoring | Insert footnote for BH10 stating more clarification in AMR on monitoring. | MOD
189 | N/A | Matter 10 - Delivery & Monitoring | Separate out targets for BE2 and BE3 over two lines and reference ‘no net loss’ as appropriate. | MOD
190 | N/A | Matter 10 - Delivery & Monitoring | Amend reference to A4/A5 as of changes to UCO for BE4 | MOD
191 | N/A | Matter 10 - Delivery & Monitoring | Remove target for proportion of A1/A2 due to UCO changes/proposed modifications to policy. | MOD
192 | N/A | Matter 10 - Delivery & Monitoring | Include primary schools for concentration of take of takeaways BE5. | MOD
193 | N/A | Matter 10 - Delivery & Monitoring | Amend target for BHC5 if we amend policy BHC5 to more positively address new provision. | MOD
194 | N/A | Matter 10 - Delivery & Monitoring | Change reference for TPO’s from BGI4 to BGI2. | MOD
195 | N/A | Matter 10 - Delivery & Monitoring | Additional targets to monitor sustainable infrastructure policies BSUI1-3: o BSU1 – number of new district heat networks o BSUI2 - % of major developments in GA’s and air quality focus area which are air quality positive – also in relation to neutral outside of these areas. o BSUI3 – number of cases where the EA sustains an objection to a planning permission (0) – but rethink wording so it is more positive. | MOD

## Submitted docs
Reference | Post Hearing Action Documents
PHA_01 | Action ref 1, Natural England reg 19 HRA response
PHA_02 | Action ref 3, Covid SCI
PHA_03 | Action ref 4, Key Diagram
PHA_04 | Action ref 5, STRATEGIC and NON-S POLICIES
PHA_05 | Action ref 15, TfL car club strategy
PHA_06 | Action ref 15, parking-policy-2020-v5
PHA_07 | Action ref 16, Western Corridor Study
PHA_08 | Action ref 16, Medium Term Plan 2018 - 2022
PHA_09 | Action ref 19, Brent long term infrastructure needs
PHA_10 | Action ref 19, Appendix A, phase 1 infrastructure projects
PHA_11 | Action ref 24, Neighbourhood forum area housing figure report final
PHA_12 | Action ref 26 & 61, Intensification Corridors Background Report
PHA_13 | Action ref 29, Small sites Delivery Assumptions in the Brent Local Plan Dec 20
PHA_14 | Action ref 36, Affordable housing delivery summary gross
PHA_15 | Action ref 36, Affordable housing delivery summary net
PHA_16 | Action ref 43, Houses in Multiple Occupation Policy BH7 Note
PHA_17 | Action ref 49, OPDC statement
PHA_18 | Action ref 52, Figure 34 town centre hierarchy
PHA_19 | Action ref 54, Shisha cafe locations map nov 2020
PHA_20 | Action ref 57, Barnet views report statement
PHA_21 | Action ref 64, cemeteries capacity statement
PHA_22 | Detailed trajectory - Gross affordable housing
PHA_23 | Detailed trajectory - Net affordable housing